## Tasks Overview
Task | Description | Timeline
Static HTML/CSS Implementation
- Layout Structure | Create layout structure including header, sidebar, main content area, and footer. | 1 week
- CSS Styling | Style the layout using CSS to match the design specifications. | 1 week
- Responsiveness | Ensure responsiveness across different screen sizes using media queries. | 1 week
Pagination and Search UI
- Pagination Controls | Design and integrate pagination controls (e.g., next, previous, page numbers). | 1 week
- Search Inputs | Create search input fields and integrate them with the design. | 1 week
- JavaScript Functions | Write JavaScript functions to handle pagination navigation and simulate search functionality. | 2 weeks
Client-Side Processing Logic
- Data Filtering and Sorting | Develop client-side logic for filtering and sorting mock data. | 2 weeks
- Pagination Functionality | Implement pagination functionality to display a subset of data on each page. | 1 week
- Search Query Handling | Write functions to simulate data filtering based on search queries. | 1 week
Authentication UI
- Form Design | Design login forms, signup forms, and password reset interfaces. | 1 week
- Client-Side Validation | Implement client-side validation for form inputs. | 1 week
- Mock Authentication Logic | Develop mock authentication logic for testing purposes. | 1 week
Other Screens
- Cases Section | Create HTML files, implement layout structure, style with CSS, add interactivity, implement AJAX. | 4 weeks
- Warranty Section | Define structure, create HTML files, implement layout, style with CSS, add dynamic features. | 4 weeks
- Analytics Section | Create wireframes, HTML files, implement layout, style with CSS, integrate data visualization libs. | 4 weeks
- In-Take/Onboarding Form Section | Create HTML files, style with CSS, add client-side validation, implement AJAX if needed. | 2 weeks
Additional Tasks
- Navigation and Routing | Implement navigation between sections/pages, set up routing if using a JS framework. | 2 weeks
- Testing and Debugging | Test for responsiveness, functionality, and compatibility, debug issues, refine UI/UX. | 3 weeks
- Integrate Front-End with API | Modify front-end code to consume data from Flask API, test API integration, debug issues. | 3 weeks

## Task Detail
Main Task | SubTask | TimelIne
Static HTML/CSS Implementation: | Create the layout structure including header, sidebar, main content area, and footer.
Style the layout using CSS to match the design specifications.
Ensure responsiveness across different screen sizes using media queries.
Pagination and Search UI: | Design pagination controls (e.g., next, previous, page numbers) and integrate them into the layout.
Create search input fields and integrate them with the design.
Write JavaScript functions to handle pagination navigation and simulate search functionality.
Client-Side Processing Logic: | Develop client-side logic for filtering and sorting mock data.
Implement pagination functionality to display a subset of data on each page.
Write functions to simulate data filtering based on search queries.
Authentication UI: | Design login forms, signup forms, and password reset interfaces.
Implement client-side validation for form inputs.
Develop mock authentication logic for testing purposes.
1. Cases Section: | Create HTML files for the Cases section.
Implement the basic layout structure based on wireframes.
Style the Cases section HTML using CSS to match the design.
Add interactivity such as sorting, filtering, and pagination to the Cases section if needed.
Implement AJAX functionality for dynamic content loading or updating cases.
Ensure consistency with the overall application styling.
2. Warranty Section | Define the structure of the page, including warranty details and related information.
Create HTML files for the Cases section.
Implement the basic layout structure based on wireframes.
Style the Warranty section HTML using CSS to match the design.
Implement any dynamic features or interactions specific to the Warranty section.
Integrate any required data visualization libraries for warranty analytics.
3. Analytics Section: | Create wireframes/mockups for the Analytics section layout.
Create HTML files for the Analytics section.
Style the Analytics section HTML using CSS to match the design.
Define the structure of the page, including warranty details and related information.
Ensure consistency with the overall application styling.
Integrate data visualization libraries such as Chart.js or D3.js for displaying analytics.
Implement dynamic updates for charts based on user interactions or data changes.
In-Take/Onboarding Form Section: | Create HTML files for the form section.
Style the form section HTML using CSS to match the design.
Apply styles to form elements, including input fields, buttons, and form validation messages.
Add client-side form validation using JavaScript to validate user inputs.
Implement AJAX functionality if form submissions require asynchronous data handling.
Navigation and Routing: | Implement navigation between sections/pages using links or tabs.
Set up routing if using a JavaScript framework (e.g., React Router) for managing navigation.
Testing and Debugging: | Test each section/page for responsiveness, functionality, and compatibility across different browsers and devices.
Debug any issues related to layout, styling, or functionality.
Refine UI/UX based on feedback and testing results.
Integrate Front-End with API: | Modify front-end code to consume data from Flask API endpoints.
Replace static data with API calls for dynamic content.
Test API integration thoroughly to ensure proper data retrieval and display.
Debug any issues encountered during integration.